SOUTHERN NATURAL GAS COMPANY

Major Expansion and Abandonment Certificates

Issued Since Last General Rate Case

CP04-340-000

On May 18, 2004, Southern filed an abbreviated application requesting approval to abandon by sale to Atlanta Gas Light Company (AGLC) approximately 253.6 miles of pipeline and appurtenant facilities located between Southern’s south main and north main lines.  The pipeline segments varied in size and lengths and made up an inverted “Y” that ran north from Southern’s main line to the Atlanta metropolitan area.  Southern also proposed to construct, install and operate certain facilities consisting of approximately 6.36 miles of 30-inch pipeline that would close the gap between the two segments of its system (AGL Triangle Project). The estimated cost of the transaction was $32 million.  In conjunction with the sale, Southern and AGLC agreed to an extension of the terms of AGLC’s FT, FT-NN and CSS service agreements, on a staggered basis, between 2008 and 2015.  FERC approved Southern’s request on January 25, 2005, and held that “[t]he costs and revenues attributable to the facilities approved to be constructed . . . shall have a presumption that they may [be] treated on a rolled-in basis in future rate proceedings filed by Southern.”  The transaction was completed on March 1, 2005.  The final portion of the AGL Triangle Project was placed in service on September 15, 2005.

CP05-388-000 and -003

On June 29, 2005, Southern filed an application for authorization to construct and operate the Cypress Pipeline Project, which would consist of 176-miles of 24-inch and 30-inch pipeline, 31,050 horsepower of compression, and appurtenant facilities that would transport up to 500 MMcf/d of regasified liquefied natural gas (LNG) from an interconnection with Southern LNG Inc.’s (SLNG) Elba Island LNG terminal near Savannah, Georgia, to an interconnection with Florida Gas Transmission Company (FGT) in Clay County, Florida.  The pipeline would be constructed in three phases at an estimated cost of approximately $321 million.  Phase I consisted of 166.63 miles of 24-inch pipeline, interconnection, measurement, appurtenant, and auxiliary facilities; Phase II consisted of a new compressor station; and Phase III consists of 9.85 miles of 30-inch diameter loop and two new compressor stations.  On June 15, 2006, the Commission authorized the construction and operation of these facilities, finding that “the costs associated with Southern’s proposed project will qualify for rolled-in rate treatment when Southern makes its next NGA section 4 rate filing.”  Phase I of the project was completed and placed in service on May 1, 2007.  On July 6, 2007, Southern filed a petition to amend the certificate authorizing the Cypress Pipeline Project; specifically, Southern sought authorization to modify the Phase II Facilities to replace the authorized 10,350 horsepower gas-driven compressor unit with a 10,350 horsepower electric-driven unit at the No. 2 Compressor Station (the Brookman Compressor Station) located in Glynn County, Georgia.  FERC authorized the amendment on July 24, 2007.  Phase II was completed and placed in service on May 1, 2008. Phase III has not commenced construction and will not be placed in service before 2010.

CP06-28-000

On November 23, 2005, Southern filed an application seeking authorization to abandon approximately 6.86 miles of its 18-inch North Main Loop pipeline near its Onward Compressor Station in Sharkey County, Mississippi.  Replacement of the segment was not necessary because other line segments that ran parallel to this segment had sufficient capacity to serve existing customer requirements. FERC issued an order authorizing the abandonment on March 21, 2006.  Southern completed the abandonment on June 16, 2006.

CP06-58-000

On February 1, 2006, Southern filed an application seeking authorization to abandon in place approximately 10.91 miles of pipeline segments on its McConnells North Main Loop Segment in Tuscaloosa County, Alabama.  Southern proposed to replace the 10.91 miles of pipe it removed by constructing approximately 6.1 miles of 24-inch pipeline on its parallel 2nd North Main Loop.  Construction was estimated to cost $8.4 million.  Southern also sought authorization to abandon in place Pell City Compressor Unit No. 3 located in St. Clair County, Alabama.  Southern stated that current customers would not be affected by the abandonment of the pipeline segment or compressor unit. FERC approved Southern’s requests on July 14, 2006 and found that “it is appropriate to permit Southern to roll in the project costs as part of its transportation cost of service in the context of its next general section 4 rate proceeding absent any significant change in circumstance.” The replacement pipeline was placed in service on November 9, 2006. Southern completed the abandonment project on December 6, 2006.

CP06-114-000

On April 3, 2006, Southern filed an application seeking authorization to abandon in place approximately a 19 mile segment of its 20-inch North Main Loop Line, located in Douglas and Fulton Counties, Georgia.  Southern stated that abandonment of the 20-inch segment would not affect its ability to meet the firm requirements of its firm transportation customers. FERC approved Southern’s request on June 19, 2006.  The abandonment was completed on December 12, 2006.

CP06-145-000

On April 26, 2006, Southern filed an application seeking authorization to abandon by sale to Denbury Onshore, LLC approximately 142 miles of transmission pipelines, appurtenant facilities that extended easterly from Tensas Parish, Louisiana, to Southern’s Gwinville Compressor Station in Jefferson Davis County, Mississippi, and the services provided by those facilities. Southern also requested that FERC make a determination that, upon the sale of the facilities, neither the facilities nor the services provided would be subject to the jurisdiction of FERC.  On June 9, 2006, FERC issued an order authorizing the abandonment by sale and finding that, following abandonment, the facilities would be exempt from jurisdiction under section 1(b) of the NGA.  Southern completed the transaction on September 26, 2006.

CP06-474-000

On September 29, 2006, Southern, filed an application seeking authorization to transfer an undivided interest in pipeline capacity up to 1,175 MMcf per day in its Twin 30s pipeline (the two 30-inch pipelines that run from Southern LNG’s Elba Island LNG terminal to Port Wentworth) to Elba Express Company, LLC (EEC), an affiliate.  Southern stated that it would retain sufficient capacity in the Twin 30s pipelines to meet its contractual obligations.  On September 20, 2007, FERC issued an order approving Southern’s request to transfer an undivided interest to EEC.  The transfer will occur on or immediately before the date EEC’s Elba Express Pipeline goes into service which is anticipated to be March 2010.

CP07-19-000

On October 30, 2006, Southern filed an application seeking approval to abandon by removal its Olga Compressor Station and related facilities, located on its Main Pass/Franklinton Loop Line, offshore Louisiana.  Some of the station and its reciprocating engines were severely damaged as a result of Hurricane Katrina.  FERC approved the abandonment on May 3, 2007.  On June 4, 2007, Southern filed seeking authorization to modify the scope of work.  FERC authorized the modification on June 22, 2007. The abandonment was completed on May 15, 2008.

CP07-28-000

On December 1, 2006, Southern filed an application seeking authorization to abandon and modify certain pipeline and appurtenant facilities on its 22-inch North Main Loop Line and requesting to construct certain pipeline facilities on its 24-inch 2nd Northern Main Loop Line located in Tuscaloosa County, Alabama.  Southern proposed to abandon in place a portion of the North Main Loop Segment from Milepost 278.48 to Milepost 281.27 (2.79 miles); to abandon and remove a portion of the North Main Loop Segment from Milepost 271.65 to Milepost 278.48 (6.83 miles); to install a new 22-inch mainline gate assembly at Milepost 278.48; to install a new 12-inch blind flange to close the 12-inch crossover value at Milepost 281.02; and to install a new 20-inch crossover connection at the Black Warrior River West Header at Milepost 281.23 between the 22-inch North Main Line and the 22-inch North Main Loop Line.  Southern also requested to extend its 2nd North Main Loop Line for 6.83 miles with 24-inch pipeline from Milepost 148.93 to Milepost 155.75.   This new segment of 24-inch pipeline was to be installed in the existing location of the 22-inch pipeline that was proposed to be abandoned.  Southern stated that the installation of this segment of the 24-inch 2nd North Main Loop Line would provide sufficient capacity to continue to serve its existing customers in this area.  The cost of constructing the 2nd North Main Loop Segment was estimated to be $10.4 million.  FERC issued an order approving the abandonment and issuing a certificate on April 16, 2007.  The Commission explained that “it is appropriate to permit Southern to roll in the project costs in the context of its next general section 4 rate proceeding absent any significant change in circumstances.”  Abandonment was completed on September 2, 2007, and the facilities were placed in service on September 17, 2007.

CP07-44-000 and CP07-45-000

On December 18, 2006, Southern and Southeast Supply Header, LLC (SESH) (jointly owned by CenterPoint Energy, Inc. and Spectra Energy Corp.) filed a joint certificate application seeking to construct 269 miles of new natural gas transmission facilities.  Pursuant to the Joint Operating Agreement, SESH and Southern would own as tenants in common the first 117 miles of the project, from the Perryville Hub near Delhi, Louisiana, to an interconnection with Southern’s existing pipeline system near its Gwinville Compressor Station in Jefferson Davis County, Mississippi (Phase I).  Southern would own 140 MMcf/d of the 1.14 Bcf/d total capacity.  FERC issued an order on September 20, 2007, approving the joint application.  Service began on the Phase I facilities from MP 0.00 to MP 212.34 on September 6, 2008 and on the remainder of the facilities on September 12, 2008.

CP07-70-000

On January 26, 2007, Southern filed an application seeking authorization to abandon by removal six compressor engines at its Toca Compressor Station in St. Bernard Parish, Louisiana that failed to comply with the EPA reciprocating internal combustion engine (RICE) regulations, which require installation of emissions controls on new and existing RICE by June 15, 2007.  Southern determined that abandonment would avoid an estimated $3 million dollars to bring the engines up to code and maintenance expenses of $368,000 annually. Southern further determined that the remaining engines could supply the required horsepower to serve existing firm customers.  FERC issued an order approving the abandonment on May 21, 2007.  The abandonment was completed on June 6, 2007.

CP07-98-000

On March 16, 2007, Southern filed an application seeking authorization to abandon by sale to Atmos Energy Corp. (Atmos) 8.94 miles of its 6-inch Columbus Lateral Line, 8.94 miles of its 4- and 6-inch Columbus Lateral Loop Lines, all appurtenant facilities associated with those lines; its Columbus Meter Station, and services provided through such facilities (Columbus Lateral Facilities), located in Lowndes County, Mississippi..  Southern stated that Atmos was the only firm shipper holding capacity on the Columbus Lateral Facilities and that interruptible shippers would not be adversely affected because the sale would simply result in relocation of the existing custody transfer point for the Columbus Delivery Point. Southern also indicated that abandonment of the facilities would reduce operating expenses and avoid future maintenance expenses of approximately $42,000 per year and approximately $1,500,000 in avoided capital costs to bring the facilities up to DOT requirements.  FERC issued an order authorizing the abandonment and construction on July 19, 2007.  The abandonment was completed on April 1, 2008.

CP08-5-000

On October 5, 2007, Southern and Magnolia Enterprise Holdings, Inc. (MEHI), an affiliate of AGL Resources, filed a joint certificate application seeking authorization for Southern to abandon by sale to Magnolia an undivided interest, equivalent to 82,000 Mcf, along Southern’s following facilities: its Twin 30s Pipeline extending from Southern’s interconnection with the Elba Island LNG facility at MP 0.0 to MP 13.161; its 10 miles of 20-inch Wrens to Savannah Second Loop Line from Wentworth, Georgia, to Effingham County, Georgia; its Cypress Pipeline; and its Brunswick Pipeline extending from its Jackson Measurement Station at MP 53.8 to MP 0.0 (collectively, the Sales Facility).  The application also included the construction of new compression facilities along the Cypress Pipeline.  Magnolia would acquire the Sales Facility and lease those facilities and other pipeline facilities acquired by Magnolia from AGL Resources to Southern.  The proposal also seeks for Southern to abandon by retirement its Laurens County Meter Station in Laurens County, Georgia.  On July 17, 2008, FERC generally approved the sale-and-leaseback proposed for the project, but denied incremental rate treatment equivalent to the negotiated lease payment.  On October 2, 2008, Southern and MEHI filed a petition to amend certificate seeking authorization to amend the lease transaction approved by the Commission’s July 17 order.  FERC authorized the amendment on February 5, 2009. Southern began construction on the facilities on February 17, 2009. The facilities are projected to be placed in service in December 2009, at which the closing on the sale of the facilities will also occur.